## GIGANE
Use this form to response to ALL Questions regarding Site Log Book and contractor's progress report for the site displayed below |  |  | NO
YES
LOCATION NAME: | GIGANE
LGA NAME: | GWADABAWA
COMMUNITY NAME: | GIGANE
WORK SATRT DATE:
FACILITY TYPE: | SMBH
LOT DESCRIPTION: | TPD001_SOK_SMBH_N00091A_1_GWADABAWA/34
CONTRACTOR: | CIMMULA NIG LTD
LATITUDE:
LONGITUDE:
COMPLIANCE | COMPLIANCE QUESTIONS
| Are Lga Supervisor Coming To Site? | YES
| Are The Lga SupervisorsEffective? | NO
| Are The Lga Supervisors Paid The Supervisor Money? | NO
DITHO FOR STATE SUPERVISORS CONTRACTORS | DITHO FOR STATE SUPERVISORS CONTRACTORS
| Do They Have Qualified Personal On Site? | NO
| Are The Contractors Engaging Ruwassa Staff For Their Works? | NO
| Are The Contractor Working To Specification? | NO
| Are There Instructions Given To The Contractors? | NO
| Are The Corrections Being Done? | NO
SITE LOG BOOK | SITE LOG BOOK
| Is there a LOG BOOK in this site? | NO
| If yes: Is the LOG BOOK adequately documented? | NO
| Is this Site Accessible? | NO
If this site is NOT ACCESSIBLE, Please Give short remark on what you know responsible for this
SNo | TASKS DETAILS | STATUS
28 | Site possession
29 | Geophysical Survey
30 | Drilling and casing with development
31 | Pumping Test
32 | Water Quality analysis
33 | Grouting and Installation of pump security
34 | Tower foundation Construction
35 | Tower Construction
36 | Reticulation and Stand taps
37 | Installation of Tanks panels and ligthen protection
38 | Solar Pump Installation
39 | Testing and Disinfection
40 | Finishing
41 | Fencing & Sign Board
SNO | SITE COMMENT | STATUS
19 | Fencing & Sign Board not installed to specification.
25 | Location not feasible
26 | Casings and screens not to specification.
27 | Adequate well development not done.
28 | Pump testing not to Specification.
29 | Water quality not acceptable.
30 | Stanchion works not to specification.
31 | Reticulation not to specification.
32 | Solar Power units/ Lightening protection not to specification.
33 | Solar Pump not installed to specification.
34 | Pump security not installed to specification.

## LUKUWA RAFI
Use this form to response to ALL Questions regarding Site Log Book and contractor's progress report for the site displayed below |  |  | NO
YES
LOCATION NAME: | LUKUWA RAFI
LGA NAME: | GWADABAWA
COMMUNITY NAME: | LUKUWA RAFI
WORK SATRT DATE:
FACILITY TYPE: | SMBH
LOT DESCRIPTION: | TPD001_SOK_SMBH_N00091A_1_GWADABAWA/35
CONTRACTOR: | CIMMULA NIG LTD
LATITUDE:
LONGITUDE:
COMPLIANCE | COMPLIANCE QUESTIONS
| Are Lga Supervisor Coming To Site? | YES
| Are The Lga SupervisorsEffective? | NO
| Are The Lga Supervisors Paid The Supervisor Money? | NO
DITHO FOR STATE SUPERVISORS CONTRACTORS | DITHO FOR STATE SUPERVISORS CONTRACTORS
| Do They Have Qualified Personal On Site? | NO
| Are The Contractors Engaging Ruwassa Staff For Their Works? | NO
| Are The Contractor Working To Specification? | NO
| Are There Instructions Given To The Contractors? | NO
| Are The Corrections Being Done? | NO
SITE LOG BOOK | SITE LOG BOOK
| Is there a LOG BOOK in this site? | NO
| If yes: Is the LOG BOOK adequately documented? | NO
| Is this Site Accessible? | NO
If this site is NOT ACCESSIBLE, Please Give short remark on what you know responsible for this
SNo | TASKS DETAILS | STATUS
28 | Site possession
29 | Geophysical Survey
30 | Drilling and casing with development
31 | Pumping Test
32 | Water Quality analysis
33 | Grouting and Installation of pump security
34 | Tower foundation Construction
35 | Tower Construction
36 | Reticulation and Stand taps
37 | Installation of Tanks panels and ligthen protection
38 | Solar Pump Installation
39 | Testing and Disinfection
40 | Finishing
41 | Fencing & Sign Board
SNO | SITE COMMENT | STATUS
19 | Fencing & Sign Board not installed to specification.
25 | Location not feasible
26 | Casings and screens not to specification.
27 | Adequate well development not done.
28 | Pump testing not to Specification.
29 | Water quality not acceptable.
30 | Stanchion works not to specification.
31 | Reticulation not to specification.
32 | Solar Power units/ Lightening protection not to specification.
33 | Solar Pump not installed to specification.
34 | Pump security not installed to specification.