## GIDAN AMAMATA
Use this form to response to ALL Questions regarding Site Log Book and contractor's progress report for the site displayed below |  |  | Approved | Approved with minor amendments | Approved with major amendments | Not approved
|  |  | Cement Slurry | Bentonite
|  |  | Submersible pump | Functional generator | Dip Meter | Calibrated Container | Stopwatch
LOCATION NAME: | GIDAN AMAMATA |  | uPVC | API
LGA NAME: | GADA |  | Yes | No
COMMUNITY NAME: | GIDAN AMAMATA |  | Yes all installed with ratings as specified | Yes all installed but rating not as specified | Yes but only SQ pump installed | No Non SQ pump installed or No
WORK SATRT DATE: |  |  | Yes plumed | Yes but not plumed | No
FACILITY TYPE: | SMBH |  | Yes right type and size | Yes right type but wrong size | No
LOT DESCRIPTION: | TPD001_SOK_SMBH_N00102B_1_GADA/38 |  | Yes to specifications | Yes not to specification | No
CONTRACTOR: | MZ AND SONS NIG LTD |  | Yes with joining kit | Yes without joining kit | No
LATITUDE: |  |  | Yes with right gauge | Yes with wrong gauge | No
LONGITUDE: |  |  | Yes with sterilised bottles | Yes without sterilised bottle | No
|  |  | Yes | Yes but reduced diameter | No
CRITICAL STAGE 1
SNo | Question | Response
83 | Geophysical survey done?(sightsurveyresult) | No
84 | Material of casing/screen | uPVC
85 | Diameter of casing/screen(Inches)
86 | Casing/screen pressure rating (bar)
87 | Cased depth of the borehole/well (Meters)
88 | Equipment used for BH/Well Pumping Test | Submersible pump
89 | Time for pumping test and recovery(hours)
90 | Borehole/well Yield/Discharge (Litres/Sec)
91 | Outfall(drainage) provided during BH/Well pumping test? | Yes
92 | Dynamic water level(meters)
93 | Static water level(meters)
94 | Water samples for analysis taken by qualified personnel?
95 | REMARKS | Approved with minor amendments
COMMENT
CRITICAL STAGE 2
SNo | Question | Response
96 | Water quality analysis carried out by the Contractor?(sightreport)
97 | Name of the off,site laboratory
98 | Biological Characteristics acceptable?
99 | Chemical Characteristics acceptable?
100 | Physical Characteristics acceptable?
101 | Material used for sanitary seal/grouting | Cement Slurry
102 | Length of sanitary seal/grouting(meters)
103 | Coordinates (Smartphone)
104 | REMARKS | Not approved
COMMENT | Comment
CRITICAL STAGE 3
SNo | Question | Response
120 | If Aggregates for concrete is YES,use all numberings with B, if NO use the numberings without B
121 | Excavation for stanchion footings to specification? | No
122 | Excavation for stanchion footings and treatment house foundation to specification? | Yes
123 | Aggregates for concrete? | Yes right type and size
124 | Aggregates for concrete works with strength of blocks for treatment house? | Yes right type but wrong size
125 | Cement of good quality? | No
126 | Blinding on excavations? | Yes not to specification
127 | Concrete mix ratio? | No
128 | Concrete workable? | No
129 | Reinforcements of good quality,size and deformed type 2? | Yes but reduced diameter
130 | Bending and placing of reinforcements as in design? | No
131 | Effective cover to reinforcements provided? | No
132 | Holding Down bolts of the right size? | No
133 | HD bolts properly fixed and plumbed? | Yes but not plumed
134 | REMARKS | Approved
COMMENT | Comment
CRITICAL STAGE 4
SNo | Question | Response
105 | Base plate dimensions to specification? | Yes with wrong gauge
106 | Universal beam/column sections?
107 | Angle irons?
108 | Steel grating?
109 | Number of PVC tanks as specified?
110 | PVC tanks new
111 | Colour of tanks black?
112 | Volume of each tank as specified?
113 | Size/diameter of all pipes?
114 | Pressure rating of all pipes as specified?
115 | Solar panels new free of cracks and defects?
116 | Total wattage of panels to specification?
117 | Size/diameter of all cables as specified?
118 | REMARKS
119 | Treatment required?
COMMENT | Comment
CRITICAL STAGE 5
SNo | Question | Response
135 | Solar pump type SQ flex and CU 200? | Yes but only SQ pump installed
136 | Cable installed complete?, if NO use the numberings without B | Yes without joining kit
137 | Level Switch installed?
138 | Excavation for pump security to specification?
139 | Metal steel box of the right gauge, size and done as in the drawing?
140 | Padlocks installed on the steel box as specified?
141 | Bending and placing of reinforcements as in design?
142 | Concrete mix ratio adequate and placed as specified?
143 | Locally,assembled Lightening?
COMMENT | Comment
CRITICAL STAGE 6
SNo | Question | Response
144 | Reticulation and tap island done?
145 | System test,ran?
146 | Period of test run (Hours)?
147 | Final checks on completed stanchion done?
148 | All components of facility functional?
149 | Signpost installed?
150 | Facility fenced?
151 | Entire system disinfected?
152 | What chemical was used to disinfect the system?
153 | All components for treatment supplied and installed as specified?
154 | Treatment components functioning as specified?
155 | Final checks on completed treatment house?
156 | Post treatment water quality analysis carried out by the Contractor? (sight report)?
157 | Name of the off,site laboratory
158 | Biological Characteristics acceptable?
159 | Chemical Characteristics acceptable?
160 | Physical Characteristics acceptable?
161 | REMARKS
COMMENT | Comment
CRITICAL STAGE 7
SNo | Question | Response
162 | Valuation of work done | CRITICALSTAGE7
Comment

## GIDAN AMAMATA_Critical_Stage_Pi
STAGE 1 PICTURES
Capture geophysical survey report | Capture pumping test going on | Capture water samples being collected | Comment and attach picture for peculiar cases
STAGE 2 PICTURES
Capture water quality result | Capture grouting | Comment and attach picture for peculiar cases
STAGE 4 PICTURES
Capture at least 1 of all steel members supplied to site for stanchion | Capture all PVC tanks with at least 1 of all pipe size supplied | Capture solar panels with at least 1 of all cable size supplied | Capture footing excavation for stanchion
Capture completed footing with holding down bolts | Capture treatment house foundation
STAGE 5 PICTURES
Capture at least 1 of all steel members supplied to site for stanchion | Capture all PVC tanks with at least 1 of all pipe size supplied | Capture solar panels with at least 1 of all cable size supplied
Comment and attach picture for peculiar cases | Capture solar pump with CU 200 | Capture metal steel box for pump security
STAGE 6 PICTURES
Capture pump security being done showing, steel box, reinforcements and concrete | Comment and attach picture for peculiar cases | Capture footing excavation for stanchion
Capture completed footing with holding down bolts | Capture treatment house foundation
STAGE 6 PICTURES
Capture water flowing from taps during test run | Capture treatment components working | Capture post treatment water analysis result
Comment and attach picture for peculiar cases